## myvisit – mobile qa t
MyVisit – Mobile QA Testing
To-Do
Name | Person | Files | Status | Date | Priority | Severity | Environment | Platform | Test Type | Item ID (auto generated)
Incorrect “No Internet Connection” Message on macOS | aboleilrayan9@gmail.com | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130808195/WhatsApp%20Image%202025-06-26%20at%2021.58.11.jpeg | New / Open | 2025-06-26 | High | Critical ⚠️️ | App downloaded from App Store, Latest version | MacBook Air 13” (M3 chip), | Compatibility Testing | 2023394917
Splash screen background color incorrect on Android 10 | Mai Abu Leil | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130810677/WhatsApp%20Image%202025-06-26%20at%2011.51.47.jpeg, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130810690/WhatsApp%20Image%202025-06-26%20at%2011.54.40.jpeg, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130810792/WhatsApp%20Image%202025-06-26%20at%2011.58.08.jpeg, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130810810/WhatsApp%20Image%202025-06-26%20at%2011.49.14.jpeg | New / Open | 2025-06-25 | High | Medium | Android Emulator – MyVisit latest version | Android 10 – Pixel 3 (API 29) | Compatibility Testing | 2019075952
Appointment booking for "Egged" does not proceed and provides no feedback |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130974065/WhatsApp%20Video%202025-06-27%20at%2015.08.30.mp4, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130974207/%D7%94%D7%A7%D7%9C%D7%98%D7%AA%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-14.33.50.mov | New / Open | 2025-06-28 | High | High | MyVisit app – latest version, downloaded from App Store / Play Store | iOS 18.5 (iPhone 11, iPad), Android 10 (Pixel 3), Android 14 (Pixel 4) | Functional Testing,Usability | 2019075957
Appointment booking fails when selecting “Haifa Municipality״ |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/130989989/%D7%94%D7%A7%D7%9C%D7%98%D7%AA%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-15.48.33.mov | New / Open | 2025-06-28 | High | High | iPhone 11, iPad, Pixel 3 (Emulator), Pixel 4 (Emulator) – MyVisit latest version | iOS 18.5 (iPhone 11, iPad), Android 10 (Pixel 3), Android 14 (Pixel 4) | Functional Testing,Usability | 2019075959
Incorrect text "Jerusalem" briefly appears when selecting Bat Yam Municipality |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131007881/%D7%94%D7%A7%D7%9C%D7%98%D7%AA%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-16.30.35.mov, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131010594/WhatsApp%20Video%202025-06-27%20at%2016.46.34.mp4 | New / Open | 2025-06-27 | Low | Medium | Pixel 3, Pixel 4, iPad – MyVisit latest version | Android 10 (Pixel 3), Android 14 (Pixel 4), iPad (iOS 18.5) | GUI Testing | 2019128916
Application allows booking two appointments at the same time in different locations |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131076886/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-20.08.07.png, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131076896/%D7%94%D7%A7%D7%9C%D7%98%D7%AA%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-20.06.30.mov | New / Open | 2025-06-27 | High | Critical ⚠️️ | iPhone 11, Pixel 3, Pixel 4 – Latest version of MyVisit – App Store / Play Store | iOS 18.5 (iPhone 11), Android 10 (Pixel 3), Android 14 (Pixel 4) | Functional Testing | 2025116444
Two users can book the same appointment slot at the same time |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131078511/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-27%20%D7%91-22.46.07.png, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131078717/WhatsApp%20Video%202025-06-27%20at%2023.17.36.mp4 | New / Open | 2025-06-27 | High | Critical ⚠️️ | – Device 1: Android 10 (Pixel 3 emulator), connected via stable Wi-Fi, with the MyVisit application installed via APK. – Device 2: Android 14 (Pixel 4 emulator), also on Wi-Fi, with the latest version of the MyVisit application installed from Google Play Store. Each device was logged into the application using a different phone number to simulate independent user sessions. Both devices were synchronized to the same system time and operated under identical test conditions to ensure consistency and reliability of the results. | Android 10 (Pixel 3), Android 14 (Pixel 4) | Functional Testing | 2025128807
Users cannot update existing appointments – only cancel and reschedule manually | aboleilrayan9@gmail.com | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131082894/%D7%94%D7%A7%D7%9C%D7%98%D7%AA%20%D7%9E%D7%A1%D7%9A%202025-06-28%20%D7%91-0.39.49.mov, https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131082909/WhatsApp%20Image%202025-06-28%20at%2000.25.49.jpeg | New / Open | 2025-06-28 | High | Medium | All tested devices with latest version of MyVisit, installed from App Store / Play Store | Android 10 (Pixel 3), Android 14 (Pixel 4), iOS 18.5 (iPhone 11, iPad) | Usability Testing | 2025181081
Unexpected “Service Unavailable” error during booking process |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131083847/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-28%20%D7%91-1.29.40.png | New / Open | 2025-06-28 | High | High | iPad, iOS 18.5, Latest version from App Store | iOS | Functional Testing | 2025203045
Top Bar Overlapping Screen Content |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131084131/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-28%20%D7%91-1.51.57.png | New / Open | 2025-06-28 | Medium | Medium | iPad, iOS 18.5, App downloaded from App Store | iOS | GUI Testing | 2025209019
No Timeout Trigger After User Inactivity |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131100634/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-28%20%D7%91-12.16.08.png | New / Open | 2025-06-28 | Medium | Medium | myVisit app, screen: ID entry / ID type selection | Android 10 & Android 14 (Emulator) | Security Testing,Functional Testing, | 2025330698
Connection error during concurrent access causing the app to crash |  | https://maiabuleil00s-team.monday.com/protected_static/30115618/resources/131128820/%D7%A6%D7%99%D7%9C%D7%95%D7%9D%20%D7%9E%D7%A1%D7%9A%202025-06-28%20%D7%91-12.59.53.png | New / Open | 2025-06-28 | High | Critical ⚠️️ | All tested devices running latest version of myVisit app | Android 10 (Pixel 3), Android 14 (Pixel 4), iPhone 11, iPad (iOS 18.5) | Load Testing,Functional Testing | 2025346844
2025-06-25 to 2025-06-28

## myvisit – mobile qa t-updates
MyVisit – Mobile QA Testing | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
2019075952 | Splash screen background color incorrect on Android 10 | Update |  | Mai Abu Leil | 26/June/2025 10:14:01 PM | On Android 10 (Pixel 3), when launching the MyVisit app, the splash screen appears with a white background and orange logo, which is inconsistent with the correct design. On all other platforms (iPhone 11, iPad, Mac, and Android 14), the splash screen displays correctly with an orange background and white logo. This inconsistency may indicate a rendering issue specific to older Android versions, and can affect branding and visual consistency. | 0 |  | 428882121
2019075957 | Appointment booking for "Egged" does not proceed and provides no feedback | Update |  | Mai Abu Leil | 27/June/2025 02:47:17 PM | When attempting to book an appointment for the service provider "Egged", on all tested platforms (iPhone, iPad, Android 10, Android 14), the user taps on "Egged", a loading animation (three dots) appears for a few seconds, but then nothing happens. The screen does not continue to the next step, and no error message or feedback is provided. This causes user confusion and blocks access to the service. | 0 |  | 429142303
2019075959 | Appointment booking fails when selecting “Haifa Municipality״ | Update |  | Mai Abu Leil | 27/June/2025 03:51:29 PM | Appointment booking fails when selecting “Haifa Municipality״ | 0 |  | 429175926
2019128916 | Incorrect text "Jerusalem" briefly appears when selecting Bat Yam Municipality | Update |  | Mai Abu Leil | 27/June/2025 04:41:02 PM | When selecting "Bat Yam Municipality" as a service provider in the MyVisit app, the screen first displays the word "Jerusalem" at the top of the screen before transitioning to the page asking for the user’s ID number. This issue was observed on Android 10, Android 14, and iPad (iOS 18.5). The incorrect city name creates confusion for the user and may indicate a data or rendering issue in the app's flow. | 0 |  | 429200536
2023394917 | Incorrect “No Internet Connection” Message on macOS | Update |  | Mai Abu Leil | 26/June/2025 09:36:42 PM | When launching the MyVisit app on MacBook Air 13 (2025), the message “No internet connection. Please check your connection and try again.” appears, even though the internet is working properly. The user verified the connection by browsing Google and other websites. This indicates that the app fails to detect an active internet connection on macOS. | 0 |  | 428876930
2025116444 | Application allows booking two appointments at the same time in different locations | Update |  | Mai Abu Leil | 27/June/2025 10:27:59 PM | During testing, I used two separate devices (Android 10 and Android 14) to access the MyVisit app. On both devices, I logged in using the same phone number, which is used by the system to identify the user. I scheduled an appointment with Israel Post in Nof HaGalil at 11:10 AM, and simultaneously booked another appointment with Bituach Leumi in Kiryat Shmona at the exact same time. The application did not display any warning or prevent the double booking, even though both appointments were tied to the same phone number. | 0 |  | 429356322
2025128807 | Two users can book the same appointment slot at the same time | Update |  | Mai Abu Leil | 27/June/2025 11:12:30 PM | The system was tested on two Android devices running Android 10 (Pixel 3) and Android 14 (Pixel 4), with each session authenticated using a distinct phone number to simulate two different users. Both users accessed the MyVisit application concurrently and proceeded to schedule an appointment with Israel Post at the same branch and for the same time slot (e.g., 11:10 AM). The application allowed both appointments to be scheduled successfully without triggering any warning, conflict message, or validation block. This behavior reveals a critical deficiency in the system’s real-time slot allocation mechanism, as it fails to enforce mutual exclusivity of time slots across users. The expected functionality is that once a time slot is selected and confirmed by one user, it should immediately become unavailable to other users. The actual behavior demonstrates that multiple users can book the same slot simultaneously, leading to potential overbooking, operational inefficiencies, and loss of trust in the system's reliability. | 0 |  | 429359153
2025181081 | Users cannot update existing appointments – only cancel and reschedule manually | Update |  | Mai Abu Leil | 28/June/2025 12:44:08 AM | The behavior was tested on multiple platforms, including Android 10 (Pixel 3), Android 14 (Pixel 4), iPhone 11, and iPad, all running the latest version of the MyVisit application. After successfully scheduling an appointment (e.g., with Israel Post or a government office), the user is presented with a confirmation screen. On this screen, the only available option is to cancel the appointment. There is no option to edit, reschedule, or update the existing appointment — such as changing the time, date, or location. The expected behavior is that the system would allow the user to modify an active appointment without the need to cancel and start over. However, the actual result is that the user must cancel the current appointment entirely and then go through the full booking process again to select a new time or location. This limitation negatively impacts usability, increases user effort, and may lead to frustration or scheduling errors | 0 |  | 429365496
2025203045 | Unexpected “Service Unavailable” error during booking process | Update |  | Mai Abu Leil | 28/June/2025 01:10:52 AM | While attempting to book an appointment in the MyVisit application, the process was interrupted by an unexpected error message stating: "Sorry, this service is temporarily unavailable." This occurred after selecting a service and time slot, just before final confirmation. The error appeared suddenly without prior indication that the service was inactive or full. The issue was reproduced on an iPad running iOS 18.5, using the latest version of the app. The expected result is that services which are unavailable should be marked as such before the user begins the booking process, either grayed out or labeled “unavailable”. The actual result is that the user completes most of the flow, only to receive an abrupt rejection message at the end. This creates confusion, wastes user time, and results in a poor experience — especially for users with accessibility or time constraints. | 0 |  | 429367934
2025209019 | Top Bar Overlapping Screen Content | Update |  | Mai Abu Leil | 28/June/2025 11:09:05 AM | The test was performed on an iPad running iOS 18.5 after launching the myVisit application and navigating to a screen that displays a top header (toolbar). Expected result: The top header should be displayed correctly, separated from the content area, without overlapping or hiding any part of the interface. Actual result: The top header overlaps part of the screen content — including the loading dots — making the screen appear empty or frozen. As a result, the user may believe the app is unresponsive. | 0 |  | 429412111
2025330698 | No Timeout Trigger After User Inactivity | Update |  | Mai Abu Leil | 28/June/2025 12:24:21 PM | After opening the app and reaching the ID entry or ID type screen, no user interaction was performed for 15 minutes. The app remained on the same screen with no timeout message, no session expiry alert, and no automatic redirection. This could expose sensitive user information if the device is unattended. Steps to Reproduce: 1. Open the app 2. Navigate to ID entry screen (e.g. Israel Electric or Ministry of Foreign Affairs) 3. Leave the screen inactive for 15+ minutes 4. Observe system behavior. Expected Result: After 5–10 minutes of inactivity, the app should either: – Display a timeout warning – Automatically return to home screen – Terminate session. Actual Result: App stays on the screen indefinitely with no timeout behavior or security mechanism triggered. Attachments: | 0 |  | 429419824
2025346844 | Connection error during concurrent access causing the app to crash | Update |  | Mai Abu Leil | 28/June/2025 01:06:56 PM | During simultaneous testing on multiple devices (Android 10, Android 14, iOS), all devices displayed the same error message: "Connection Error – Unable to connect with the server. Check your Internet connection and try again." This issue likely results from the app server being unable to handle multiple user requests at the same time. When multiple users attempt to connect simultaneously, the backend seems to become unresponsive, leading to a failure in establishing a connection. Additionally, pressing the "Try again" button does not resolve the issue, indicating a lack of proper retry or recovery mechanism. 🧪 Steps to Reproduce: --------------------- * Launch the myVisit app on multiple devices concurrently. * Navigate to the homepage or ID entry screen. * Wait for the initial loading process. * Observe if a connection error message appears across devices. ✅ Expected Result: ------------------ The app should manage concurrent requests gracefully. In case of temporary server unavailability, it should: >* Display an appropriate message indicating high traffic, * Automatically retry the request after a delay, * Or load cached/fallback content. ❌ Actual Result: ---------------- All tested devices display a connection error message. No data is loaded, and retry attempts fail. The app becomes unusable until manually restarted. | 0 |  | 429425836